## Working
WG | Standard | Vers | Date | Status | Task Driver | Expected Release | Dependency | Notes
DAL | TAP - Table Access Protocol (Rel) | v1.1 | 2019-04-20 | RFC | Querying catalogues remotely | Summer 2019
DAL | SLAP - Simple Line Access Protocol | v2.0 | 2019-04-09 | WD | VAMDC Accessing lines |  | pending SSLDM-2.0
DM | SSLDM v2.0 | v2.0 |  | WD | VAMDC Accessing lines
DAL | ObsLocTAP - Observation Locator Table Access Protocol | v0.4 | 2019-02-27 | WD | XMM-Newton, Integral, Chandra Coordinating observations between facilities | May 2020
DAL | ObjVisSAP - Object Visibility Simple Access Protocol | v0.5 | 2019-03-19 | WD | XMM-Newton, Integral, Chandra Coordinating observations between facilities | May 2020
DAL | ProvTAP - Provenance Table Access Protocol | v0.1 | 2019-03-22 | WD (Internal) | CTA, Pollux, SVOM, MuseWise, CDS DB, triple Store Accessing provenance DM through TAP. Also useful for ML |  | Provenance v1.0
DM | Provenance | v1.0 | 2018-10-15 | PR | CTA, Pollux, SVOM, MuseWise, CDS DB, triple Store Accessing provenance DM through TAP. Also useful for ML
DAL | ProvSAP |  |  | Authors writing | CTA, Pollux, SVOM, MuseWise, CDS DB, triple Store Accessing provenance DM through TAP. Also useful for ML |  | Provenance v1.0
DAL | Datalink | v1.1 |  | Discussion | Data discovery Links to further data
DAL | DALI - Data Access Layer Interface | v1.2 |  | Discussion | Core standard to support other DAL standards. Allow DAL standards to do things consistently IVOA infrastructure
DAL | ADQL - Astronomical Data Query Language (Rel) | v2.1 | 2017-12-08 | WD | Community Input |  |  | ?? Rel vs. NonRel
DM | Coordinates model | v1.0 | 2019-03-20 | WD | CSP priority Multi Dimension use case Needed for the Cubes Search for space, time and Coordinates Partial replacement of STC
DM | Transform model | v1.0 | 2019-04-12 | WD | CSP priority Multi Dimension use case Needed for the Cubes Search for space, time and Coordinates Partial replacement of STC
DM | Measurement model | v1.0 | 2019-05-01 | WD | CSP priority Multi Dimension use case Needed for the Cubes Search for space, time and Coordinates Partial replacement of STC
DM | Cube v1.0 | v1.0 |  | WD (Internal) | CSP priority Multi Dimension use case Search for space, time and Coordinates |  | pending CoordTransMeas v1.0
DM | VODML-Mapping | v1.0 | 2018-05-01 | WD | IVOA Infrastructure Needed to serialize IVOA DMs
DM | DatasetMetadata v1.0 | v1.0 |  | WD (Internal) | Generalized DM for datasets Link with CAOM ? Multi Dimension phase 2 |  | pending Meas v1.0
DM | Translation of DMs to VODML/VODML modeling utilities | ?? |  | ?? | IVOA Infrastructure
DM | SourceDM | v1.0 |  | New | Gaia, Chandra DM for catalogues Data discovery for sources |  | Use cases / Example/Requirements from catalogs | CSP
DM | TimeSeries |  |  | New | Comparing light curves |  | pending Cube v1.088
GWS | Group Membership Service 1.0 | v1.0 | 2019-05-06 | WD | User authorization Data sharing between groups of users
GWS | VOSI Best Practice |  |  | Note | IVOA Infrastructure
GWS | VOSI | v2 |  | Errata (Working) | IVOA Infrastructure
GWS | Science Platforms |  |  | New | Bring the code to the data Share data and code among users Collaborative virtual environment
Reg | RegTAP | v1.1 | ?? | ?? | IVOA Infrastructure TAP query to the IVOA Registry
Reg | STC in Registry | ?? | ?? |  | Identify the coverage of the VOResources in the Registry |  | dependent on STC
Semantics | Maintenance of the list of UCD words | V2.0 | 2018-08-23 | RFC | IVOA infrastructure
Semantics | UCD1+ controlled vocabulary | V1.3 | 2018-02-19 | PR | IVOA infrastructure
Few notes: | Green = vote at May TCG F2F
Yellow = in RFC
Cols with ?? Need input
All columns/rows need a check
Notes | Radio??

## Done
WG | Standard | Version | Help?? | Date | Status | Task Driver | Expected Release | Dependency | Notes
DAL | SODA-1.0 | 1.0_Err-1 |  | 2019-04-18 | Errata | Community Input | 2019-05-01
DM | Obscore 1.1 | v1.1 |  | 2018-12-19 | Errata |  | 2019-05-01
Reg | VOResource-1.1 | v1.1 |  | 2019-03-05 | Errata |  | 2019-05-01
Reg | Discovering Data Collections Within Services | v1.1 |  | 2019-03-22 | Note |  | 2019-05-01