DAL Summary
TAP
  - WD 0.5 published on 18/05/2009
  - Last remaining issues resolved during this Interop:
    - Enlisted the aid of VOTable and G&WS WGs
    - VOTable WG:
      - MIME type in VOTable
      - TAP field attribute
    - G&WS:
      - Extend UWS job description schema

---
TAP
  - Intention is to develop TAP prototypes demonstrating both ADQL and PQL querying
  - PQL document must follow the normal IVOA approval procedures
  - TAP V1.0 not coupled to PQL V1.0 any more than it is to ADQL
  - TAP expected to meet its schedule

---
TAP Schedule:
  - WD 1.0 5/6/09
  - WG review 5/6/09-3/7/09
  - PR 3/7/09
  - RFC 6/7/09-21/8/09
  - TCG review 24/8/09-19/9/09
  - Exec review 21/9/09-2/10/09
  - REC 5/10/09

---
PQL:
  - PQL V0.1 (17/02/2009) contained elements already discussed within the context of TAP
    - Therefore, although a recent document, the contents have already undergone some scrutiny
  - PQL V0.2 published very recently (22/05/2009) and so needs review
    - Depending upon material differences, with effort from DAL WG, PQL should progress rapidly through the approval process
  - I therefore urge the DAL WG to maintain the efforts of late to complete the PQL review process.

---
SLAP/SSLDM 0.9 WD published
  - Good discussion and agreement during Interop
  - PR 1.0 to be published 5/6/09
  - RFC 5/6/09
SIAP V1.0
  - (Currently V1.1 due to technical hitch!)
  - Moved to PR
  - RFC period started

---
SIAP V2
  - Long discussion in Interop
  - Many new features
  - WD “any day soon”
SSAP
  - Lower level of activity since Baltimore
  - But some investigations under way
Footprint Services
  - Again, lower level of activity since Baltimore

---
Conclusion:
  - TAP to enter RFC 5/6/09
  - PQL to receive rigorous review
  - SLAP/SSLDM to enter RFC 5/6/09
  - SIAP V1 in RFC
  - SIAP V2 WD very soon
  - SSAP low level activity
  - Footprint Services low level of activity

---
Conclusion:
  - TAP to enter RFC 5/6/09
  - PQL to receive rigorous review
  - SLAP/SSLDM to enter RFC 5/6/09
  - SIAP V1 in RFC
  - SIAP V2 WD very soon
  - SSAP low level activity
  - Footprint Services low level of activity
My thanks to everyone for all the hard work and compromise